#### HURRICANE KATRINA SITUATION REPORT		9/2/05			0800 HOURS PST

Page 1 of 2

I. Situation Summary:

##### Federal & Region

- 28 Urban Search and Rescue (USAR) teams are in Louisiana and Mississippi.  Operations have ceased in New Orleans until National Guard can assist with security.  1,778 total US&R assets deployed.

13 Hazardous Materials Teams have been deployed.

- 43 National Disaster Medical System Teams (NDMS) with 1,196 personnel are deployed in the region.

- AMTRAK is developing a plan to initiate evacuations by train.

- 4 million Meals-Ready-to-Eat (MREs) will be deployed over the next three days into the region.

###### Louisiana

- Civil unrest is basically under control in Orleans and Jefferson, according to Jeff Parish Emergency Operations Center Director Walter Maestri.

- Patient evacuation efforts have been severely hampered by security concerns, but continue at a slow pace.  NDMS teams in the area (Superdome and I-10 Causeway) were removed as a result of security concerns.

- Health and Human Services is working to identify sufficient staff and equipment to support a 1000 bed mobile hospital capability.  500 of these beds are being provided by the Department of Defense (DoD), with remaining capacity coming from other Emergency Support Function (ESF) partners.

- 1 DPMU with 1 DMORT is in operation in Baton Rouge.  6,200 body bags have been delivered to the Baton Rouge facility and an additional 22,000 will be sourced.  Current plans are to process and bury bodies, in body bags, in a location to be chosen by the Louisiana Governor, to be turned into a memoriam.

II. Weather Forecast:

|  | Fri | Sat | Sun | Mon |
| --- | --- | --- | --- | --- |
| General | Sunny | Sunny | Sunny | Sunny |
| High/Low | 95°/75° | 95°/73° | 93°/74° | 90°/72° |
| Precip. Chance | 20% | 20% | 20% | 20% |

III. Current Actions:

CATF-3 (Swift Water Rescue) is currently in a stand down mode due to security issues.  They’re waiting for Military support before redeploying.  In the past two days, they’ve rescued approximately 400 people.  They report some support logistical problems, but are addressing these within the team.  This team is being housed at Camp Shelby, which is the New Orleans Saints Training Camp.

There’s no cell phone service in the area.  Our deployed members cannot call out unless they locate a hard line.

CATF-1 (USAR) stayed in Dallas last night. They are currently en route to La Fayette Louisiana.

Civilians overran the Riverside USAR Team and many of their supplies were stolen.

# HURRICANE KATRINA SITUATION REPORT		9/2/05			0800 HOURS PST

Page 2 of 2

Texas agreed to triple to 75,000 the number of evacuees being taken in from Louisiana. Houston officials temporarily stopped admitting people to the Astrodome late Thursday after accepting 11,325. Others will be housed in the adjacent Reliant Center, where the Houston Texans play football.

Military helicopters on Thursday dropped about 150 massive sandbags into the levee breach that allowed flood waters from Lake Pontchartrain to pour into New Orleans.

The 3,000-pound sandbags are part of a temporary plan aimed at plugging the hole in the levee. The Corps also plans to drop concrete highway dividers and seal the spot where swirling waters undermined and toppled the floodwall, said Brig. Gen. Robert Crear, commander of the crew working to fix the floodwall. "We're dumping things into the hole, just to stem the tide".

IV. Miscellaneous Important Information:

Fatalities (Confirmed):		No current update available for this report.

| Louisiana | Mississippi | Alabama | Florida | Texas | Total |
| --- | --- | --- | --- | --- | --- |
| 3 | 13 | 2 | 11 | 1 | 30 |

Security:

CNN producer Jim Spellman, who has been stationed with police sharpshooters, says

reports indicate that New Orleans officers are not showing up for work. In some districts

as many as 60 percent of officers have not reported for duty.

Electricity:				No current update available for this report.

2,257,329 million customers are still without power.

Communications:

There’s no cell phone service in the area.  Our deployed members cannot call out unless they locate a

hard line.

Shelters: 				No current update available for this report.

343 shelters are open and staffed.

82,852 people are in shelters.

Situation Report Prepared by LAFD Special Operations Division, Homeland Security Intelligence Section